## Product Backlog
Product Backlog
Identifier | Name | Priority | Refinement State | Detail in file | End points | Parameters | Response | User Stories
ID001 | Add new admin | Implement in Next Sprint | Groomed | ID001_Add_new_admin.feature | POST | name,email,password,balance,isAdmin | Auto generated id | As an admin I want to add new employee account So the new employ can have admin access
ID002 | Add new user // Sign-up | Implement in Next Sprint | Groomed | ID002_Add_new_user.feature | POST | name,email,password,balance,isAdmin | Auto generated id | As a person who wants to be physically active I want to be a Fit Garage user So I can attend the Fit Garage workout classes
ID003 | Get user info | Implement in Next Sprint | Groomed | ID003_Get_user_info.feature | GET | Id, name | Users in JSON format | As an admin I want to retrieve all information from a user So I can contact him
ID004 | Remove existing user | Implement in Next Sprint | Groomed | ID004_Remove_existing_user.feature | DELETE | Id | (status) | As an inactive member I want to delete my Fit Garage account So I can clean my memberships
ID005 | Change user attributes | Implement in Next Sprint | Groomed | ID005_Change_user_attribute.feature | PATCH | name,email,isAdmin | fields which changed | As an active user I want to change my email address So I can receive notifications on my main address
ID006 | Update user password | Implement in Next Sprint | Groomed | ID006_Update_user_password.feature | PATCH | email, password | (status) | As a user of Fit Garage I want to change my current password So I can access my account with a new password
ID007 | Add money to balance | Implement in Next Sprint | Groomed | ID007_Add_money_to_balance.feature | PATCH | Balance | Balance | As my account balance is empty I want to add some money So I can book more workout classes!
ID008 | Admin Adds Workout Class | Implement in Some Future Sprint | Not Groomed |  | POST | title, startTime, endTime, instructor, location, enable(boolean) | auto generated id | As an admin I want to add a workout class So users can enroll in that class
ID009 | Admin Disables Enrollement to Workout Class | Implement in Some Future Sprint | Not Groomed |  | PATCH | id, enable | (status) | As an admin I want to disable the option to enroll into a workout class So users can not enroll in that class until it is enabled again.
ID010 | Admin Enables Enrollement to Workout Class | Implement in Some Future Sprint | Not Groomed |  | PATCH | id, enable | (status) | As an admin I want to enable the option to enroll into a workout class So users have the option enroll in that class.
ID011 | Admin Deletes Workout Class | Implement in Some Future Sprint | Not Groomed |  | DELETE | id | (status) | As an admin I want to delete a workout class So users can no longer enroll in that class.
ID012 | Admin Updates Workout Class attributes | Implement in Some Future Sprint | Not Groomed |  | PATCH | title, startTime, endTime, instructor, location | changed fields | As an admin I want to update the attributes of a workout class So that the users see the updated attributes.
ID013 | Query all workout classes | Implement in Some Future Sprint | Not Groomed |  | GET | NONE | All workout classes in JSON format | As an active user I want to look at all workout available So I can register for one
ID014 | Query workout classes by parameter | Implement in Some Future Sprint | Not Groomed |  | GET | startTime, location, instructor | List of workout classes in JSON format | As an active user I want to look at particular workout available So I can register for one suiting my expectations
ID015 | User Enrolls in Workout Class | Implement in Some Future Sprint | Not Groomed |  | POST | workoutClassId, userId | (status) | As an active user I want to enroll in a workout class So I can attend the class
ID016 | User Drops Workout Class | Implement in Some Future Sprint | Not Groomed |  | DELETE | workoutClassId, userId | (status) | As an active user I want to drop a workout class So that I am no longer enrolled in that class
ID017 | User create review of workout class | Implement in Some Future Sprint | Not Groomed |  | POST | ReviewId, UserId, WorkoutClassId, grade, review comment | (status) | As a user who loved a class I want to make a review to that class So I can make this workout more attractive
ID018 | User edits review of workout class | Implement in Some Future Sprint | Not Groomed |  | PATCH | ReviewId, UserId, WorkoutClassId, grade, review comment | (status) | As a user who is going regularly to a workout I want to change my review as the workout improved So I can make this workout more attractive
ID019 | Query workout reviews | Implement in Some Future Sprint | Not Groomed |  | GET | WorkoutClassId | grade and reviews in JSON format | As a user looking for a new workout I want to read the reviews So I can choose the most popular workout
ID020 | Delete a review | Implement in Some Future Sprint | Not Groomed |  | DELETE | ReviewId | (status) | As a workout class got cancelled I want to delete the associated reviews So I can free us database spaces
ID021 | Creating a GitHub | Implement in Next Sprint | Groomed
ID022 | Make a KANBAN for tasks | Implement in Next Sprint | Groomed
ID023 | Finalize Database schema | Implement in Next Sprint | Groomed
ID024 | Add a README.md file | Implement in Next Sprint | Groomed
ID025 | Create and connect PostgreSQL database (test db connection) | Implement in Next Sprint | Groomed
ID026 | Create and Configure React-Django project | Implement in Next Sprint | Groomed
ID027 | Setting up Home Page | Implement in Some Future Sprint | Not Groomed
ID028 | Setting up routing from home to other pages | Implement in Some Future Sprint | Not Groomed
ID029 | Setting up sign up/log in pages | Implement in Some Future Sprint | Not Groomed
ID030 | Use Figma for UI Mockup | Implement in Some Future Sprint | Not Groomed
ID031 | Implementing a Navigation/Tool Bar | Implement in Some Future Sprint | Not Groomed
ID032 | Writing description for each available course | Implement in Some Future Sprint | Not Groomed
ID033 | Choosing Website Theme | Implement in Some Future Sprint | Not Groomed
ID034 | Setting up the Booking Page | Implement in Some Future Sprint | Not Groomed
ID035 | Implementing booking features | Implement in Some Future Sprint | Not Groomed
ID036 | Write unit tests for backend | Implement in Some Future Sprint | Not Groomed

## Sprint A Backlog
SPRINT BACKLOG:
Identifier | Name | Priority | Refinement State | Detail in file | End points | Parameters | Response | User Stories
ID001 | Add new admin | Implement in Next Sprint | Groomed | ID001_Add_new_admin.feature | POST | name,email,password,balance,isAdmin | Auto generated id | As an admin I want to add new employee account So the new employ can have admin access
ID002 | Add new user // Sign-up | Implement in Next Sprint | Groomed | ID002_Add_new_user.feature | POST | name,email,password,balance,isAdmin | Auto generated id | As a person who wants to be physically active I want to be a Fit Garage user So I can attend the Fit Garage workout classes
ID003 | Get user info | Implement in Next Sprint | Groomed | ID003_Get_user_info.feature | GET | Id, name | Users in JSON format | As an admin I want to retrieve all information from a user So I can contact him
ID004 | Remove existing user | Implement in Next Sprint | Groomed | ID004_Remove_existing_user.feature | DELETE | Id | (status) | As an inactive member I want to delete my Fit Garage account So I can clean my memberships
ID005 | Change user attributes | Implement in Next Sprint | Groomed | ID005_Change_user_attribute.feature | PATCH | name,email,isAdmin | fields which changed | As an active user I want to change my email address So I can receive notifications on my main address
ID006 | Update user password | Implement in Next Sprint | Groomed | ID006_Update_user_password.feature | PATCH | email, password | (status) | As a user of Fit Garage who forgot his password I want to change my online password So I can connect again to my account
ID007 | Add money to balance | Implement in Next Sprint | Groomed | ID007_Add_money_to_balance.feature | PATCH | Balance | Balance | As my account balance is empty I want to add some money So I can book more workout classes!
ID008 | Admin Adds Workout Class | Implement in Some Future Sprint | Not Groomed |  | POST | title, startTime, endTime, instructor, location, enable(boolean) | auto generated id | As an admin I want to add a workout class So users can enroll in that class
ID009 | Admin Disables Enrollement to Workout Class | Implement in Some Future Sprint | Not Groomed |  | PATCH | id, enable | (status) | As an admin I want to disable the option to enroll into a workout class So users can not enroll in that class until it is enabled again.
ID010 | Admin Enables Enrollement to Workout Class | Implement in Some Future Sprint | Not Groomed |  | PATCH | id, enable | (status) | As an admin I want to enable the option to enroll into a workout class So users have the option enroll in that class.
ID011 | Admin Deletes Workout Class | Implement in Some Future Sprint | Not Groomed |  | DELETE | id | (status) | As an admin I want to delete a workout class So users can no longer enroll in that class.
ID012 | Admin Updates Workout Class attributes | Implement in Some Future Sprint | Not Groomed |  | PATCH | title, startTime, endTime, instructor, location | changed fields | As an admin I want to update the attributes of a workout class So that the users see the updated attributes.
ID013 | Query all workout classes | Implement in Some Future Sprint | Not Groomed |  | GET | NONE | All workout classes in JSON format | As an active user I want to look at all workout available So I can register for one
ID014 | Query workout classes by parameter | Implement in Some Future Sprint | Not Groomed |  | GET | startTime, location, instructor | List of workout classes in JSON format | As an active user I want to look at particular workout available So I can register for one suiting my expectations
ID015 | User Enrolls in Workout Class | Implement in Some Future Sprint | Not Groomed |  | POST | workoutClassId, userId | (status) | As an active user I want to enroll in a workout class So I can attend the class
ID016 | User Drops Workout Class | Implement in Some Future Sprint | Not Groomed |  | DELETE | workoutClassId, userId | (status) | As an active user I want to drop a workout class So that I am no longer enrolled in that class
ID017 | User create review of workout class | Implement in Some Future Sprint | Not Groomed |  | POST | ReviewId, UserId, WorkoutClassId, grade, review comment | (status) | As a user who loved a class I want to make a review to that class So I can make this workout more attractive
ID018 | User edits review of workout class | Implement in Some Future Sprint | Not Groomed |  | PATCH | ReviewId, UserId, WorkoutClassId, grade, review comment | (status) | As a user who is going regularly to a workout I want to change my review as the workout improved So I can make this workout more attractive
ID019 | Query workout reviews | Implement in Some Future Sprint | Not Groomed |  | GET | WorkoutClassId | grade and reviews in JSON format | As a user looking for a new workout I want to read the reviews So I can choose the most popular workout
ID020 | Delete a review | Implement in Some Future Sprint | Not Groomed |  | DELETE | ReviewId | (status) | As a workout class got cancelled I want to delete the associated reviews So I can free us database spaces
ID021 | Creating a GitHub | Implement in Next Sprint | Groomed | 0
ID022 | Make a KANBAN for tasks | Implement in Next Sprint | Groomed | 0
ID023 | Finalize Database schema | Implement in Next Sprint | Groomed | 0
ID024 | Add a README.md file | Implement in Next Sprint | Not Groomed | 0
ID025 | Create and connect PostgreSQL database (test db connection) | Implement in Next Sprint | Not Groomed | 0
ID026 | Create and Configure React-Django project | Implement in Next Sprint | Not Groomed | 0

## Scratch
Priority | Refinement state
Implement in Next Sprint | Groomed
Implement in Some Future Sprint | Not Groomed